## Slide 1: Program objectives
To improve access to oral pre-exposure prophylaxis (PrEP) as part of the combination HIV prevention package for adolescent girls and young women (AGYW)
To improve oral PrEP knowledge awareness among AGYW.
To increase uptake, continuation and effective use of oral PrEP through client centred, acceptable and differentiated service delivery models
To strengthen risk awareness and risk reduction counselling for AGYW
To build the capacity of health facilities to provide client centred oral PrEP
To monitor and evaluate implementation of PrEP in the district.

## Slide 2: PrEP Initiations Oct’ 21 – Dec 21
Chart: 
| Oct'21 | Nov'21 | Dec'21
 | 376 | 329 | 194

## Slide 3: PrEP Return 1 month Average retention at month 1- 78%
Chart: 
| Oct'21 | Nov'21 | Dec'21
PREP_NEW | 252 | 178 | 131
1 mnth | 159 | 149 | 102
% | 0.63095 | 0.83708 | 0.77863

## Slide 4: PrEP Initiations by Client Profile
Chart: 
| M | F | M | F | M | F | M | F | MSM | SW | SERO | PSUNK | OTHER
 | 0 | 128 | 82 | 107 | 0 | 0 | 97 | 485

## Slide 5: PrEP Initiations by Facility
Chart: 
| Mvurwi | Bare | Nzvimbo | Rosa | Henderson | Concession | Mazowe Mine | Tsungubvi | Dambo | Suwoguru | Forrester | Nyakudya | Jingamvura | Davaar | Holme Eden | Mazoe Citrus | Makope | Belgownie | Christon Bank | Ardura | Cranham | Shopo | Horta | Donje | Mazowe Sec | Von Abo | Shutu | Mazowe Prison
PREP-NEW | 301 | 192 | 153 | 142 | 129 | 127 | 99 | 98 | 82 | 81 | 77 | 72 | 71 | 68 | 59 | 59 | 58 | 58 | 58 | 56 | 51 | 45 | 43 | 42 | 38 | 28 | 27 | 23

## Slide 6: Percentage achievement towards annual target
Chart: 
| COP20 Annual Target | Achievement
 | 1038 | 2333

## Slide 7: Targets vs Achievements by sex & age disaggregation

## Slide 8: Clients currently on PrEP as at 30 Jun’21
Chart: 
| F | M | F | M | F | SW | SERO | OTHER
 | 465 | 326 | 708 | 178 | 1183

## Slide 9: HIV status at 3 months for PREP_CURR
Total on PrEP – 2,861
Total HIV status – 2291
Variance- 588 (20%)
Some clients were not retained at either 1 month or 3 months AND some clients had no documented HIV status hence Total HIV Status not equal to PREP_CURR
Chart: 
| Positive | Negative | < 3 months on PrEP
 | 4 | 1594 | 679

## Slide 10: Summary of targets & achievements
PREP_CURR | Target | Achievement | % Achvmnt
Overall | 1287 | 2861 | 222%
Sex Workers | 324 | 465 | 144%

## Slide 11: Activities conducted during the COP
                PrEP expansion to 11 new facilities
PrEP treatment literacy sessions targeting AGYW.
Integrated outreaches
Community dialogues with AGYW
Support group formation- (8 support groups formed)
Collaborative activities with other partners in the district

## Slide 12: Program adaptation to unavoidable challenges
WHO guidelines on Covid 19 were observed during all activities.
Donated PPE to PrEP implementing sites
Provided PPE to our lay cadres
Used sessions to integrate key message on how to prevent transmission.
Virtual mobilization for PrEP uptake was done by PrEP Champions
Service provision at the community through integrated outreaches.